## Sheet1
Member | Date | Efforts (Describe what you did)
alrich.f | 2025-06-02 | Made a gantt chart
Alexey S. | 2025-06-02 | Set up Logbook & Group 3 Teams chat
Alexey S. | 14/2/2025 | Group discussion to sort out roles and things to talk about the PIP presentation
Krishna | 14/2/2025 | Made flowchart for typical organisational structure that we can use as inspiration
Alexey S. | 19/2/2025 | Group discussion to finalise PIP presentation
James | 19/2/2025 | Made the PIP Presentation
Alexey S. | 26/2/2025 | Came up with a rocket design concept and theory behind it
Arthur M. | 26/2/2025 | Made CAD models for the first design; cone + fin designs
Pablo | 26/2/2025 | Researched on possible aerodynamic designs
Arthur M. | 2025-02-03 | Further development for fin design
Prabesh | 2025-05-03 | Did extensive research on materials for rocket design, with sources
James | 2025-05-03 | Added onto Prabesh's research
Pablo | 2025-03-05 | Researched into cheap, resistant and reliable materials
Arthur M. | 2025-11-03 | Called a meeting to discuss progress.
Alexey S. | 23/3/2025 | Made 7 Nosecone designs in SW for the calc team to do flow testing on.
Alrich | 24/3/2025 | Performed Flow Simulation on aforementioned nose cones
Partha | 25/3/2025 | Called a meeting to discuss next steps. Discussed potentiality for launch simulation to be done in the Sim suite
Alexey S. | 26/3/2025 | Made progress report presentation
Sam B. | 27/3/2025 | Presents progress report presentation note: others were absent during this time so sam and arthur get credit
Arthur M. | 27/3/2025 | Presents progress report presentation
Sam B. | ?/3/2025 | Presents strong template for website hosted locally using React based web dev stack. Simply requires details at this point
Partha | 2025-03-04 | Creates simulated water bottle accurate in dimensions in CAD (for final assembly)
James | 20/4/2025 | Gathered measurements for all existing nosecones and predictions for how they will perform
Partha | 30/04/2025 | Creates sleeve for fins for rocket in CAD
Arthur M. | 30/04/2026 | Creates fins for rocket in CAD
Alexey S. | 30/04/2027 | Creates final nosecone design in CAD
Partha | 30/04/2028 | Creates final assembled rocket in CAD
Pablo | 2025-07-05 | Summons meeting to discuss next steps. Next steps are figured out
Alexey S. | 2025-07-05 | Organizes team's next steps and assigns tasks to individuals
Alexey S. | 7/52025 | Creates assembly drawing for rocket
Alrich | 2025-07-05 | Creates part drawings for rocket and Final checks for all CAD files
James | 2025-10-05 | Came up with the final measurements for the rocket
Pablo | 13/52025 | Completed the risk assesment with help from alrich
Sam B. | 2025-10-05 | Advances on the website template, creating a professional design and implementing data collected from other teams.
Sam B. | 2025-10-05 | Hosts website externally through Vercel so it is no longer only available locally.
James | 14/10/2025 | Ran additional lab tests on thrust and recorded the data
Pablo | 14/10/2025 | Ran additional lab tests on thrust and recorded the data
Sam B. | 22/05/2025 | Finishing touches on website including adding the 10 minute video and updated calculations.
Partha.s | 18/05/2025 | Resized the nose cone as it did not fit the bottle with the Micro:bit
alrich.f | 16/05/2025 | Filmed the video with external help from a friend and pictures of the team
alrich.f | 19/05/2025 | edited the video using movavi video editing software
alrich.f | 13/05/2025 | created a PDS for the project
alrich.f | 19/05/2025 | Recoding the micro:bit for slight adjustment before the launch
Alexey S. | 16/05/2025 | Made the marketing poster for the project